## Slide 1
Jo Air Contact Centre - State of Play 2024
Performance has declined across all core KPIs for the second consecutive year.
This presentation summarises the current state, root causes, and recommended programme.
Audience: Senior Leadership Team | Date: Q3 2024

## Slide 2
Current Performance vs Target
FCR: 46% Target: 65% CRITICAL
AHT: 7.6 min Target: 5.5 min CRITICAL
CSAT: 2.9/5.0 Target: 4.0 CRITICAL
Agent Attrition: 38% Industry: 18% CRITICAL
Escalation Rate: 33% Target: 15% CRITICAL
IVR Containment: 19% Target: 45% CRITICAL
No single metric is on target.

## Slide 3
Why Performance Is Declining
1. Agents use 8-11 separate systems per contact - no unified desktop
2. Knowledge base has not been updated in 12 months
3. Supervisor ratio degraded from 1:15 to 1:24 after headcount cuts
4. Quality variance between BPO sites - 18 point gap Manila vs Dublin
5. IVR redesign project stalled - customers defaulting to live contacts
6. GDPR compliance training at 68% - 3 regulatory breaches in 18 months

## Slide 4
Financial Impact
Cost per contact: £8.40 (was £6.20 in 2022) - 35% increase
Estimated annual cost of failure: £4.2M in excess handle time
Disruption event Aug 2023: estimated £1.8M in reputational cost
Customer churn attributable to service failure: approx 12,000 customers
Total quantifiable cost of current state: £6M+ per annum

## Slide 5
Recommended Programme
Track 1: Unified Agent Desktop - 18 month programme, £2.1M investment
Track 2: BPO Quality Standardisation - 6 months, in-house delivery
Track 3: IVR Self-Service Rebuild - 9 months, £0.8M investment
Track 4: Supervisor Capability Restoration - 3 months, £0.4M
Track 5: Compliance Remediation - 30 days, mandatory
Total investment: £3.3M | Projected annual saving: £5.1M | ROI payback: 8 months